## Ok As Is (hidden)
QC Issue ¦ Dev Response | Screenshot | File Name
QC: Pop-up content mismatches with base course content. Refer screenshot Dev: Ok as is, as per unit3 we are maintaining consistency and Unit3 is already approved by client. | http://180.151.87.232/bttool/qcfiles/Greenhouse Gas Management Institute Revisualization and localization US21838 44493_alpha_03_11_2016_T08_01_30.jpg | Greenhouse Gas Management Institute Revisualization and localization US21838 44493_alpha_03_11_2016_T08_01_30.jpg
QC: Highlighted screen is missing from course. All such screens are missing from course. Please fix this globally. Dev: Ok as is, as per client requirement we have removed assessment/exercise. | http://180.151.87.232/bttool/qcfiles/Greenhouse Gas Management Institute Revisualization and localization US21838 44493_alpha_28_10_2016_T11_08_31.jpg | Greenhouse Gas Management Institute Revisualization and localization US21838 44493_alpha_28_10_2016_T11_08_31.jpg
QC: Highlighted letters should be in lowercase. Dev: We have corrected the grammatical changes(For e.g. capitalize of first letter after period and colon). | http://180.151.87.232/bttool/qcfiles/Greenhouse Gas Management Institute Revisualization and localization US21838 44493_alpha_28_10_2016_T08_10_31.jpg | Greenhouse Gas Management Institute Revisualization and localization US21838 44493_alpha_28_10_2016_T08_10_31.jpg
QC: Screen 26 and 27 of reference course are missing in the our newly created course. Dev: Ok as is, as per client requirement we have removed assessment/exercise.
QC: Text Mismatch in OST. Dev: Ok As Is...SB was updated according to the text.
QC: Arrow correspond to "No inspection specified is missing. Dev: ok as is client provided
QC: Color of last icon in the screen should be red in colour as per SB. Refer screen shot. Dev: Discussed with ID this is fine
QC: A separate screen should be created for content of these PPT slides as per instructions in SB. Dev: Discussed with ID this is fine
QC: Content of PPT slide 68 and 69 should not be merged. PPT slide 69 should merge with content of PPT SLide 70 and 71. Dev: Discussed with ID and this is fine
QC: Use green color ticks instead of red colored. Dev: Ok as is as per discussed with ID.
QC: Replay button is not working. Dev: Ok as is, it is as per previous course
QC: If we click any of the template button for example, help or glossary, then on closing it learner is not able to attempt for question, as radio buttons are not working. And struck on those screens. Dev: for all the cyu we are using a single template in which external audio is playing. as we have limited access over external audio this can not be possible.

## Release Notes
Here are sample release notes that you can pick and update for respective course as applicable.
Sno. | Note | Remarks
1 | Functionality of this course will work as per the previously released course to customer. Here is the SVN path of reference course.
2 | Audio used is scratch audio. Please do not check for pronunciation related issues in audio. Do a broad level mapping only to ensure that all paragraphs in audio transcript are spoken in the audio.
3 | The audio is to be mapped with audio script and not SB because we have not updated the SB for changes done in the audio a per ID/customer feedback. NOTE to development team: If this note is not shared, QC will map the audio text with SB and all mismatches will be considered closed if the source of mapping is changed in next round post issues pointed by QC.
4 | Lip syncing of mentor/character in this course is para to para instead of word by word.
5 | Videos used in course are client provided and there is no need to check for the quality of these videos except that they are loading and running fine in the course. We will not modify anything in these videos. 1. Topic# Page# 2. … … … …
6 | Images used on following screens are client provided. We will not modify anything in these images. 1. Topic #_Page # 2. … … … …
7 | Images on following screens are picked from Shutterstock. We will not edit those images and will use them as is. The translated content will not appear on these images. Customer is made aware of this deviation. 1. Topic #_Page # 2. … … … …
8 | Map viz notes in SB. NOTE: By default, QC does not map the viz notes. Their focus is to test the sceen from user perspective. Viz notes section should be closed within devlopment teams.
9 | Some images used in the course may differ from SB however, they are approved by media and ID teams. Please do a basic hygiene check on all the images but do not map them with SB.
10 | Bold formatting in SB will not be followed in course because of font style constraint.
11 | Formatting of content (bold/italic/underline) as per SB will not followed in course. Instead, we have maintained consistency within course for formatting of i-text as per previously singed off modules. Please refer the SVN path given below of the reference course: <SVN Path>
12 | The forced functionality feature is applicable on entire course except following instances: 1. Learn More button can be clicked in any sequence at any time. 2. Clicking on Learn More buttons, info button, note icon are not included in forced functionality 3. ... ... ...
13 | Following functionality/feature will differ from previous series of same course due to updates received from customer. Provide list of changes/deviation here:
14 | Following feedback is received from customer during SB review and we have incorporated the changes directly in course. Course will deviate from SB at following instances: 1. Topic#Page#: Interactivity functionality is changed as follows-> …….. 2. Topic #Page#: iText is modified to say-> ... ... ... 3. ... ... ... ... ...
15 | Share list of open issues that are unresolved at development's end and inputs from customer is awaited. PDF/popup/any downloadable content on screens x,y,z are awaited.
16 | Technology limitation (Storyline/lectora/flash/HTML5 limitation) <Dev team to specify any tool limitation here. To start with QC team has collated some S/W constraints in the xls below, however, this list is not yet formally approved by media team. Please specify any additional constraints that is not part of this list and applicable to the course. Please note that some of the issues in this list are not S/W constraint, however, if dev manager has decided not to fix them due to time constraint then mention the relevant reason for keeping such issues as open upfront.> In absence of release notes, QC will raise them as issues. | S/W Constraint
17 | Branching: On the click of Prev/Back button, screen will jump to the Last Visited page instead of immediate previous page.
18 | For Scorm testing, use Wisdom LMS because client use the same.
19 | Following URL will open on Client's Intranet only. Please note that those links will not work in our environment. Only map the URL with SB for these screens: <Mention screen number where this is applicable>
20 | For conversion projects: Following features in course will deviate from base course because we have maintained consistency with ## units/modules of this course which is client approved: 1. …Standard instruction text in popup is modified as follows: ______________.... 2. …Client has got following pages removed for the newly constructed course. Here is the mail from customer for reference. <Provide SVN path> 3. ...Blatant grammatical errors have been fixed in the newly constructed course as per updates received from ID... 4. ... ... ... ...
21 | The translated content for following screen(s) has been picked from mail received from customer. Please map the content from the email placed at following location on SVN: <SVN path here> | Minimize such exceptions and instead update the SB to include content provided by customer in the SB itself to avoid any inconsistency in other series of same course.
22 | In translated/localized courses following items are not translated/localized: 1. Buttons name/tip text appearing on screen 2. Confirmation popup appearing on Exit button click. 3. Images content because images are not editable. 4. … … …
23 | PSD is not the updated one on SVN. Please use following OS browser combinations for testing: 1. Win 7 IE11 2. Win 7 IE 9 3. … … … …

## CHD
Hi! Welcome to Course Handover Document
1. Global Guidelines: Please avoid special characters in the project name, course name, release notes or any part of the CHD. Special characters to avoid are: @, "", "'", ~ etc. 2. In case the CHD form throws errors, please follow the guidelines given in the following screenshot.
* Mandatory Fields
Project Name * | Provide correct Project name along with PIN details. If you do not see the project listed, please connect with SEPG team to get the respective project assigned to you.
Project Manager * | Provide correct Project manager's name here.
Course Title * | Provide correct course name here. This will be used as module name on BT tool while logging bugs. Please do not club multiple modules here.
Start Date * | Not applicable; Removed now.
Course Level * |  | Choose correct course level as applicable for respective course.
Functional Manager[ID] * | Provide correct ID FM name here.<Kanchan Pandey/Pushpali Deb Kaushal/Shalini Sharma/Ritu Bhattacharya/Shivangi Saxena> Write ''NA'' if ID function is not involved in respective course's development. For example, localization courses will have this field ''NA''.
Developer Names[ID] | Choose all ID names who have worked on this project and are accountable for quality of the course.
Functional Manager[Med] * | Provide correct Media FM/Lead name here. <Madhu Rajput/Ramesh Bist/Asif Ali Khan/Kavita Sachdeva/Rafiuzzaman Khan> Write ''NA'' if Media function is not involved in respective course's development. For example, HTML 5 courses will have this field ''NA'' unless media is involved in some development cycle in this project.
Developer Names[Med] | Choose all media developer names who have worked on this project and are accountable for quality of the course.
Functional Manager[Tech] * | Provide correct Tech/Programming FM name here. <Amit Kumar/Rakesh Gupta/Hitesh Rawat> Write ''NA'' if Tech/Programming function is not involved in respective course's development. For example, Storyline/Captivate/Lectora/...courses will have this field ''NA''. | [7 empty] | Programmer
Developer Names[Med] | Choose all media developer names who have worked on this project and are accountable for quality of the course.
Developer Names * | Provide all developer names from each function who are involved in the development of respective course.
Version * |  | Proto: Choose this when a prototype id being submitted to customer. When you choose this phase the client edits option will remain disabled. POC: Proof of concept->Use this phase when we are submitting a course with few pages for bidding a deal. When you choose this phase the client edits option will remain disabled. Alpha: Use this phase when there is 1st time submission to customer. When you choose this phase the client edits option will remain disabled. Beta: Use this phase when there is 2nd and beyond submission to customer. The client edits option will be enabled for this phase. Gold: Use this phase when there is final submission to customer including SCORM version of the course. The client edits option will be enabled for this phase.
No of HTML/Flash Pages * | Provide correct screen count of respective module submitted for testing. NOTE: In case of one CHD for a project which contains series of modules, then please mention screens count of each module separately here in advance. | We have some instances where screen count of constructed course is much less than the number of slides in SB. 1. Case to be considered: Single screen with layered content; simulations; videos; animations; popup heavy screens with each popup containing content equivalent to one page/frame/screen. To calculate frame count of such courses please use the following method: Total Frame Count = Frame count in the SB + (Audio word count of the animation/Words count per page depending on the level of course). The standard word count is L1 – 125, L2 – 135, and L3 – 150. 2. For videos, LH will the the video duration/60; use following calculation for screen count: (Video duration/60)*40
No of Slides/Pages in Storyboard * | Provide correct number of SB slides/pages here.
Learning Hours * | Total number of HTML or Flash Pages/40
Course Memory Size in MB * | Provide correct size of course folder here excluding the source size.
Scope for Testing * |  | E2E: When you choose this, following scopes (in partial testing) gets selected by default: Onscreen Text Mapping/Functionality/Audio Review/Audio Mapping/Audio Syncing/Transcript Mapping Ensure that you uncheck the not applicable options so that there is clarity to QC for applicable scope of testing. For example, if there is no audio integrated in the course and this is Alpha submission, the uncheck Audio Review, Audio Mapping, Audio Syncing checks. Regression Testing: Choose this when you want QC to verify only the client edits received at respective phase (Alpha/Beta/gold). (Note: Please do not select any additional scope in partial testing options, if only Edits regression is there.) Partial Testing: Choose this option when you have additional scope for QC along with client edits verification. For example, Audio review of complete course along with validation of Client Edits Alpha.
Partial Testing | Content mapping/Functionality/Audio review/Audio mapping/Audio syncing/Transcript mapping/Scorm 1.2/Scorm 2004/AICC/ILT/Internal edit/Clientedit alpha/Clientedit beta/Clientedit gold/ | Choose relevant scope applicable for respective module. For 1st time feedback from customer choose Clientedit Alpha. For all subsequent submissions to customer, choose Clientedit Beta. For final/last set of changes choose Clientedit Gold. Case 1: First time submission to customer and QC then, Version = Alpha Scope of Testing = E2E Partial Testing = Onscreen Text Mapping, Functionality, Audio Review, Audio Mapping, Audio Syncing, Transcript Mapping | Case 2: First time feedback from customer where there are less number of changes received, so along with implementing changes we have also added audio to the course then, Version = Beta Scope of Testing = Partial Testing Partial Testing = Functionality, Audio Review, Audio Mapping, Audio Syncing, Transcript Mapping, Clientedit Alpha Release Notes: Please mention all exceptions clearly here. | Case 3: First time feedback from customer with huge list of changes and complete revision of course content is received. Audio is not yet recorded and added to course because of huge number of changes. All client edit fixes verification along with complete mapping is expected in this round. Version = Beta Scope of Testing = Partial Testing Partial Testing = Onscreen Text Mapping, Functionality, Transcript Mapping, Clientedit Alpha | Case 4: Second time feedback from customer with quite a few number of changes received. Audio is not yet recorded. All client edit fixes verification along with complete mapping is expected in this round. Version = Beta Scope of Testing = Regression Testing Partial Testing = Functionality, Clientedit Beta | Case 5: Second (and beyond) time feedback from customer with few number of changes received. Audio is recorded. All client edit fixes verification along with audio testing is expected in this round. Version = Beta Scope of Testing = Partial Testing Partial Testing = Functionality, Audio Review, Audio Mapping, Audio Syncing, Transcript Mapping, Clientedit Beta | Case 6: Final feedback from customer with few number of changes received. SCORM is implemented. All client edit fixes verification along with SCORM testing is expected in this round. Version = Gold Scope of Testing = Partial Testing Partial Testing = Functionality, Audio Review, Audio Mapping, Audio Syncing, Transcript Mapping, Clientedit Beta, Scorm #/AICC testing (Select as applicable.) | Case 7: SCORM delivery to customer for old course which would have been delivered to customer years back or some time back by GCube. Only SCORM testing is expected in this round. Version = Gold Scope of Testing = Partial Testing Partial Testing = Functionality, Scorm #/AICC testing (Select as applicable.)
Confirmation On Reviews * | ID Review Internal, GD Review Signoff Internal, Programming Review Signoff Internal, Peer Review, Functional Review, ID Signoff | Components should be signedoff by respective functions post selv review and before it is submitted to QC. Choose relevant option here. Peer review without functioonal signoff, if selected, should have exception from DM and SPM.
Test Environment(OS, browsers and devices) | Specify complete set of OS-Browser combinations where testing is to be performed as per customer requirement. Select all applicbale environment here. In case one off the selected devices is applicable, please mention this information in release notes clearly to QC.
Course Path [SVN] * | Provide correct and complete SVN path of the course to be tested.
SB Path [SVN] * | Provide correct and complete SVN path of the latest storyboard to be referred to including the respective file name. Provide correct and complete SVN path of the base course provided by customer to be referred to as applicable.
Edit Sheet * | Provide correct and complete SVN path of the client edit sheet where development team has populated their comments for each client edit received. Ensure that all edits are categorized as Enhancement/G-Cube miss.
Development Tracker Path [SVN] * | If more than one developer is involved in development of any course then share clear segregation of respective screens developed by respective developer so that issues could be assigned to correct person.
Updated PSD Path [SVN] * | Share the updated PSD path of respective course on SVN which has been followed while development.
Test Case/Checklists [SVN] * | Generic Test cases SVN path: http://192.168.2.4/content3/QC/Checklist/Updated Checklist/QC Generic Test Cases_V2.xlsx <Provide project specific customized test cases path that you have used for self review. In absence of customized checklist, you can use applicable checkpoints from generic test cases.>
Comments / Release note information | Refer to the Release Notes tab for samples and add all applicable release notes for respective course here. Mention all applicable release notes here for the respective course.
Attach/Embed supporting documents | Provide any supporting document here. Better to place all supporting documents on SVN and share the path in CHD.
Note on B8: Refer to description in next cell at right side.
Note on B16: Refer to description in next cell at right side.
Note on B21: Refer to description in next cell at right side.