## BIBC to CCA Project
Course code | SCP/RIA/DIP/Content | Platform | Details of Bug/issue | CR # | CR Status | Course Status | Comments from R&D
all BIBC | RIA | Samsung Galaxy | Print link does not work on Samsung |  | None | Device issue, not fixable
all BIBC | RIA | Samsung Galaxy | Advance on mode not working |  | None | could not reproduce in 2.3.30
all BIBC | RIA | Samsung Galaxy | When the auto advance mode is off, the pause button does not turn to Replay button after completing any section within the slide and also at the end of the slide. |  |  |  | R&D (David Leahy - 20/03/2014) - This issue was not replicated when tested with RIA player 2.3.30 (latest RIA player delivered to CDPs on 18/03/2014)
all BIBC | RIA |  | Pause button does not change back to Replay |  | None | could not reproduce in 2.3.30 | as above
all BIBC | RIA | All platforms | Audio on/Off button is not working on all tablet devices. | n/a | n/a | Can release as is | standard player behaviour, should not be logged going forward
all BIBC | content | Desktop | Lisping like, low audio quality in Desktop "Video off" mode | n/a | n/a | To be logged as an edit when encountered | R&D - under investigation
all BIBC | content | Desktop | Audio volume level differences in scenes | n/a | n/a | If significant volume difference is found, log as level 1. If a minor volume difference is heard log as level 2
all BIBC | content | All platforms | Text for lesson objectives missing |  |  | Can release as is | BI/CHs do not have lessons, this issue is not valid.
Localised BIBC | RIA | All platforms | Transcript appears blank on localised courses (transcript button should only be available on ENUS). | ? |  | Can release as is. No need to log going forward | The transcript button will be removed from localized BI/BCs, no date for the change yet - may be in 2.4
German CH |  | Samsung Galaxy | The sign > should not overlap the letter n of durchgehen. For reference see grab attached. | n/a | n/a | Can release as is | Testers had text size set to 125%
French ch/bi? |  | All platforms | Help page- Aperçu des tests link : Please insert space between dans and Progression et tests |  |  |  | R&D - software QA is testing the issue and following up with SFA to get more details. Test was done on IE9 and issue is not replicated.
_pc_bi_lcbi004 | Content | Ipad | Cannot open video | 160650 | Closed NPTF | edit fixed. Log edits like this going forward | MP4 file regenerated. Issue due to missing Data Rate and Data Size tags
_pc_ch_isch001 | RIA | Samsung Galaxy | Pop up email text overlap | 161176 | Is Duplicate bug | course is WIP in SFA | Fixed, to release in 2.4.21
_pc_ch_isch001 | RIA | Samsung Galaxy | Text overlaps (container in wrong location) | 161176 | Is Duplicate bug | course is WIP in SFA | Fixed, to release in 2.4.21
_pc_ch_isch001 | RIA |  | Timer wrapping onto second line | n/a | n/a | Can release as is | Testers had text size set to 125%
_pc_ch_isch001 | RIA |  | Solution text cropped | n/a | n/a | Can release as is | Testers had text size set to 125%
_pc_ch_isch001 | both |  | Solution question options not shuffled | n/a | n/a | Can release as is | As designed
_pc_bi_pabi009 | SCP | Desktop | Graphics not appearing in non-video mode | 160586 | Verification pending | course is signed off | Fixed in 7.11
_pc_ch_sach016 | RIA | Ipad | No scrollbar in caption area | 161351 | As designed | course is signed off | Closed, As designed (i.e. use built-in tablet scrolling capability)
_pc_ch_sach020 | RIA |  | Image does not appear correctly | 161354 | Open (reopened) | course is signed off | Fixed, to release in 2.4.21